## Ark2
Web site development project Lofthus frukt og saft
|  |  | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
Task name | Responsible | Resources | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Over all project | bar: Week 1 T to Week 4 F
Client startup meeting | Pm | Pm, Fed,Cm | Week 1 M: 2
Kick-off | Pm | Pm,Team | Week 1 T: 2
Project status meetings | Pm | Team | Week 1 F: 0.5; Week 2 F: 0.5; Week 3 W: 0.5; Week 3 F: 0.5; Week 4 M: 0.5; Week 4 W: 0.5; Week 4 TH: 0.5
Final launch and delivery meeting | Pm | Team, Cm | Week 4 F: 4
Planning | bar: Week 1 T to Week 1 F
Must have/Epics | Pm | Pm,Team | Week 1 T: 5
Site structure/Functions | Pm, | Fed, Fed2 | Week 1 W: 7
Marked resaerch | Cw | Cw | Week 1 W: 2; Week 1 TH: 2; Week 1 F: 2
Design | bar: Week 1 TH to Week 2 F
Design: Style tile | Fed | Fed | Week 1 TH: 4; Week 1 F: 3; Week 2 M: 2; Week 2 T: 4
|  | Fed2 | Week 1 TH: 4; Week 1 F: 3; Week 2 M: 2; Week 2 T: 4
Design: Appearance and use | Fed | fed | Week 1 TH: 4; Week 1 F: 3; Week 2 M: 2; Week 2 T: 4
|  | Fed2 | Week 1 TH: 4; Week 1 F: 3; Week 2 M: 2; Week 2 T: 4
Customer Approval meetings | Fed | Fed,Fed2,Cm | Week 2 M: 3
Infrastructure tasks | bar: Week 1 T to Week 2 M
Domain name desision | Pm | Pm,Cm | bar: Week 1 T
Domain name registration | Pm | Pm | Week 1 W: 0.5
Ordering domain hosting and assign access | Pm | Pm | Week 1 W: 1.5
Odrering and setting up certificate for SSL |  |  | Week 1 TH: 0.5; Week 2 M: 0.5
Webshop development | bar: Week 2 M to Week 4 W
Text content | Cw | Cw | Week 2 M: 3; Week 2 T: 3; Week 2 W: 3; Week 2 TH: 3; Week 3 TH: 2
Photos/images | Ph | Ph | Week 2 W: 4; Week 2 TH: 4; Week 3 TH: 3
|  | fed2 | Week 2 W: 4
Html and Css | Fed | Fed | Week 2 W: 5; Week 2 TH: 5; Week 2 F: 4; Week 3 M: 4; Week 3 T: 4; Week 3 W: 3; Week 3 TH: 4; Week 3 F: 4
Customer Approval meetings | Fed | Fed, Cw, Ph, Cm | Week 3 W: 3
User interaction | bar: Week 2 M to Week 4 W
Text content | Cw | Cw | Week 3 M: 3; Week 3 T: 3; Week 3 W: 3; Week 3 TH: 2
Photos/images | Ph | Ph, | Week 2 M: 3; Week 2 T: 3; Week 3 TH: 3
|  | Fed2 | Week 2 W: 4
Html and Css | Fed2 | Fed2 | Week 2 TH: 5; Week 2 F: 3; Week 3 M: 4; Week 3 T: 4; Week 3 W: 3; Week 3 TH: 3; Week 3 F: 2
Customer Approval meetings | Fed2 | Fed2, Cw, Ph, Cm | Week 3 W: 3
Promotion | bar: Week 2 M to Week 4 W
Text content | Cw | Cw | Week 2 W: 3; Week 2 TH: 4; Week 3 W: 3; Week 3 TH: 4; Week 4 M: 5
Photos/images | Ph | Ph, | Week 3 M: 6; Week 3 T: 6; Week 4 M: 7
|  | Fed2 | Week 3 M: 2; Week 3 T: 2
Html and Css | Fed2 | Fed2 | Week 2 TH: 3; Week 2 F: 3; Week 3 W: 4; Week 3 TH: 4; Week 3 F: 5; Week 4 M: 7
Customer Approval meetings | Fed2 | Fed2,Cw, Ph, Cm | Week 3 F: 3
Customer approval meetings
Approval meetings content | Cw | Cw, Ph,Cm
Approval, test and adjustment meeting | Pm | Team,Cm
Last minute critical adjustments | Pm | Team | Week 4 T: 7; Week 4 W: 7; Week 4 TH: 7
Resources | Alias | Name | Week 1 M: Work; Week 1 T: After CM feedback; Week 1 SU: Project phases; Week 2 F: Covers user stories
Customer | Cm |  | Week 1 M: Hours; Week 1 T: Hours; Week 1 SU: Webshop development; Week 2 F: all pages and content for product presentation and sale
Project manager | Pm | Bolt | Week 1 M: Hours; Week 1 T: Hours; Week 1 SU: User interaction; Week 2 F: all pages and content for user interaction like contact, review etc.
Front-end-develpoer | Fed | Aud | Week 1 M: Hours; Week 1 T: Hours; Week 1 SU: Promotion; Week 2 F: all pages and content for company promotion
Copywriter | Cw | Thea | Week 1 M: Hours; Week 1 T: Hours
Photographer | Ph | Kristin | Week 1 M: Hours; Week 1 T: Hours
Front-end-developer2/digital desinger | Fed2 | Raymond | Week 1 M: Hours; Week 1 T: Hours
Team | pm,fed,cw,ph,dd
Legends
Customer meetings | Hours
Team meetings | Hours
Project status meetings | Hours
Approval meeting | Hours
Project phase duration
Available extra time
Last minute Critical adjustments | Hours